## Project Work Estimates
Work Estimates Report
Generated by Gemini @ 2013-03-26 12:40
| Start Month | (All)
|  |  | Work ITems | Hours Logged | Hours Estimated | Avg. Logged | Avg. Estimate | Variance | Avg. Variance
| INTRA | In Progress | 9.231% | 1 | 13 | 0.17 | 2.17 | 12 | 0
|  | In Backlog | 6.154% | 4 | 6 | 1 | 1.5 | 2 | 0
|  | Tested | 4.615% | 15.5 | 45 | 5.17 | 15 | 29.5 | 0
|  | Parked | 4.615% | 5 | 12 | 1.67 | 4 | 7 | 0
|  | In Sprint | 3.077% | 0 | 0 | 0 | 0 | 0 | 0
| INTRA Total |  | 27.69% | 25.5 | 76 | 1.42 | 4.22 | 50.5 | 0
| IMS | In Progress | 18.46% | 50.52 | 69 | 4.21 | 5.75 | 18.48 | 0
|  | Unassigned | 40% | 11.5 | 0 | 0.44 | 0 | -11.5 | 0
|  | Assigned | 13.85% | 20 | 0 | 2.22 | 0 | -20 | 0
| IMS Total |  | 72.31% | 82.02 | 69 | 1.75 | 1.47 | -13.02 | 0
| Grand Total |  | 100% | 107.52 | 145 | 1.65 | 2.23 | 37.48 | 0
Data!R2:R1
Data!S2:S1
Note on XET41: R1 and R2 contain formulae that this sheet depends on

## Data (hidden)
IssueKey | Project Name | ProjectCode | Title | Description | Reporter | Resources | Status | Priority | Severity | Resolution | Type | Revised | Created | Closed Date | Resolved Date | Due Date | Start Date | Percent Complete | Comments | Estimated Effort | Points | Component | FixedInVersion | AffectedVersionNumbers | Age | Repeated | Excess Time | Remaining Time | Time Logged | Votes | Visibility | Count() | Start Month | Due Month | Estimated Hours | Estimated Minutes | Actual Hours | Actual Minutes
[33 empty] | 01-00 | 01-00 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Note on AH1: Calculated column NOT FROM Data

## Definitions (hidden)
Fields: | IssueKey | ProjectName | ProjectCode | Title | Description | Reporter | ResourceNames | Status | Priority | Severity | Resolution | Type | Revised | Created | ClosedDate | ResolvedDate | DueDate | StartDate | PercentComplete | Comments | EstimatedEffort | Points | ComponentNames | FixedInVersion | AffectedVersionNumbers | Age | Repeated | ExcessTime | RemainingTime | TimeLogged | Votes | Visibility | Count()
Url: | http://localhost/Gemini/project/INTRA/17/planner
Date: | 2013-03-26 12:41
Name: | Manager .